## Practice list
Area | Practice Code | Practice Name | Address | Approx Go-Live
Wishaw | 62671 | Dr. Clark & Partners | Wishaw Health Centre Kenilworth Ave Wishaw, ML2 7BQ | 2010-07-06
Wishaw | 62929 | Dr. A. Connelly | Wishaw Health Centre Kenilworth Ave Wishaw, ML2 7BQ | 2010-07-07
Uddingston | 63813 | Dr. Bowman & Partners | Lincluden Surgery 53 Bellshill Rd Uddingston, G71 7PA | 2010-07-09
Wishaw | 62666 | Dr. McKay & Partners | Wishaw Health Centre Kenilworth Ave Wishaw, ML2 7BQ | 2010-07-13
Wishaw | 62914 | Dr. Maule & Partners | Wishaw Health Centre Kenilworth Ave Wishaw | 2010-07-15
Bargeddie | 63832 - Branch site | Drs. Russell, Young & Abedin | 56 Abercrombie Crescent Bargeddie G69 7SP | 2010-07-27
Viewpark | 63832 | Drs. Russell, Young & Abedin | Viewpark Health Centre 119 Burnhead St Viewpark | 2010-07-27
Viewpark | 63828 | Dr Anne MacAlister & partners | Viewpark Health Centre 119 Burnhead St Viewpark, G71 5SU | 2010-07-29
Motherwell | 62609 | Dr. Rose (Mishra?) & Partners | 41 Ladywell Road Motherwell | 2010-08-03
Wishaw | 62967 | Dr. Murphy & Partners | Wishaw Health Centre Kenilworth Ave Wishaw, ML2 7BQ | 2010-08-05
Motherwell | 62717 | Dr. Liddle & Partners | Modyrvale Medical Centre, Toll St,Motherwell | 2010-08-10
Newmains | 62806 | Dr. Dear & O'Riordan | Newmains Health Centre 17 Manse Rd Newmains | 2010-08-17
East Kilbride | 63508 | Dr Walker | Alison Lea Medical Centre Calderwood E.K. | 2010-08-19
East Kilbride | 63279 | Greenhills Medical Practice | Greenhills Health Centre 20 Greenhill Sqre E.K. | 2010-08-24
East Kilbride | 63531 | Dr Deehan | Alison Lea Medical Centre Calderwood E.K. | 2010-08-25
East Kilbride | 63301 | Dr T. B. Matthew and Partners | 50 The Murray Road E.K. | 2010-08-26
Motherwell | 62736 | Dr. Lando & Partners | Motherwell Health Centre 134-138 Windmillhill St Motherwell | 2010-08-31
Hamilton | 63461 | Dr. Lynas & Partners | 53 Burnbank Road Hamilton | 2010-09-01
Motherwell | 62702 | Drs. Kerr & Keenan | Motherwell Health Centre 134-138 Windmillhill St Motherwell | 2010-09-07
Motherwell | 62789 | Dr. McBride | Motherwell Health Centre 134-138 Windmillhill St Motherwell | 2010-09-09
Motherwell | 62685 | Dr.Tilley | Motherwell Health Centre 134-138 Windmillhill St Motherwell | 2010-09-14
Motherwell | 62793 | Dr. Sturgeon & Partners | Motherwell Health Centre 134-138 Windmillhill St Motherwell | 2010-09-16
Motherwell | 62690 | Dr. Bell | Motherwell Health Centre 134-138 Windmillhill St Motherwell, ML1 1TB | 2010-09-21
East Kilbride | 63315 | Dr. Chisholm & Partners | Alison Lea Medical Centre Calderwood E.K. | 2010-09-23
Airdrie | 61061 | Dr. Clements & Partners | Adam Avenue Clinic South Nimmo Street Airdrie ML6 6DN | 2010-09-29
Chapelhall | 62596 - Branch | Salburgh branch | Community Centre, Salisburgh, ML7 4LR | 2010-09-30
Chapelhall | 62596 | Chapelhall practice | 30 Lauchope Street Chapelhall, ML6 8SR | 2010-09-30
Airdrie | 61127 | Dr Dunn & McIntyre | Airdrie Health Centre, Monkscourt Avenue Airdrie, ML6 0JU | 2010-10-05
Airdrie | 61131 | Dr. Lough & Partners | Airdrie Health Centre, Monkscourt Avenue Airdrie, ML6 0JU | 2010-10-07
Law Village | 62933 - Branch site | Dr. Logan & Partners | The Surgery Shawfiled Crescent Law, ML8 5JH | 2010-10-12
Wishaw | 62933 | Dr. Logan & Partners | Wishaw Health Centre Kenilworth Ave Wishaw, ML2 7BQ | 2010-10-12
Airdrie | 61471 | Dr Glen | Airdrie Health Centre, Monkscourt Avenue Airdrie, ML6 0JU | 2010-10-14
Airdrie | 61471 - Branch site | Dr Glen | Millstream Surgery, 50 Main Street, Caldercruix, ML6 7RA | 2010-10-14
Coatbridge | 61216 | Dr. Ooi | 9 Centenary Gardens Coatbridge, ML5 4BY | 2010-10-19
Airdrie | 61428 | Dr Lees | Airdrie Health Centre, Monkscourt Avenue Airdrie, ML6 0JU | 2010-10-21
Carluke | 62219 | Dr. Workman & Partners | The Health Centre, 14 Market Place Carluke, ML8 4AZ | 2010-10-26
Carluke | 62223 | Dr. J.F.N. Stewart | The Health Centre, 14 Market Place Carluke, ML8 4AZ | 2010-10-28
Biggar | 62312 | Dr Goldie & partners | Health Centre, South Croft Rd Biggar, ML12 6BE | 2010-11-02
East Kilbride | 63320 | Dr. H McNeil | Alison Lea Medical Centre Calderwood E.K. | 2010-11-02
Lanark | 62510 | Dr. Flowerdew & Partners | 71 Ayr Road Douglas | 2010-11-11
Lanark | 62510 - branch site | Dr. Flowerdew & Partners | Rigside Surgery Ayr Road, Rigside ML11 9NP | 2010-11-11
Lanark | 62510 - branch site | Dr. Flowerdew & Partners | 41 - 43 Coalburn Road Coalburn ML11 0LH | 2010-11-11
Carstairs | 62331 | Dr Goudie Practice | The School House School Rd Carstairs, ML11 8QF | 2010-11-16
Forth | 62346 | Kingshill Medical Practice | 40 Manse Road Forth | 2010-11-18
Cumbernauld | 61343 | Dr. Norris & Partners | Central Health Centre Nth Carbrain Rd Cumbernauld | 2010-11-23
Cumbernauld | 61343 - Branch site | Dr Norris & Partners | Craigmarloch MC 17 Auchinbee Way G68 0EZ | 2010-11-23
Hamilton | 63438 | Dr Sandilands & Partners | Wellhall Medical Centre 4 Hillhouse Rd Hamilton | 2010-11-25
Hamilton | 63419 | Burnbank Medical Centre | Burnbank Medical Centre 18 Burnbank Centre Hamilton | 2010-12-02
Cumbernauld | 61339 | Dr. A S Graham & Partners | Central Health Centre Nth Carbrain Rd Cumbernauld, G67 1BJ | 2010-12-09
Hamilton | 63457 | Dr. Young & Partners | 1 Douglas Street Hamilton | 2011-01-18
Hamilton | 63476 | Dr. Barton & Partners | Cadzow Health Centre 187 Low Waters Rd Hamilton | 2011-01-25
Lesmahagow | 62632 | Dr. Christie & Partners | The Glebe Medical Centre Abbeygreen, Lesmahagow | 2011-02-01
Glenboig | 61409 | Dr. Bawa | 8 Centre Street Glenboig | 2011-02-08
Cumbernauld | 61377 | Drs. Allahabadia & Twaddle | Abronhill Health Centre Pine Rd Abronhill, G67 3BE | 2011-02-15
Blantyre | 63334 | Dr. James & Partners | Blantyre Health Centre, Victoria Street Blantyre, G72 0BS | 2011-02-22
Airdrie | 61170 | Dr. D. Walker | Airdrie Health Centre, Monkscourt Avenue Airdrie, ML6 0JU | 2011-04-19
Airdrie | 61184 | Wellwynde | Airdrie Health Centre, Monkscourt Avenue Airdrie, ML6 0JU | 2011-04-26
Airdrie | 61151 | Dr. Hamilton & Partner | The Bank House Medical Centre, 27 East High Street Airdrie, ML6 6LF | 2011-05-03
Airdrie | 61057 | Dr. Zaman | 5 Aitken Street Airdrie, ML6 6LS | 2011-05-03
Airdrie | 61038 | Dr T.Idrees | Clarkston Medical Centre 114 Forrest St. Airdrie, ML6 7AG | 2011-05-10
Bellshill | 62031 | Dr. McKenna & Partners | Bruce Medical Centre, 2 Pollock Street, Mossend, Bellshill, ML4 1QD | 2011-05-10
Coatbridge | 61288 | Dr. Singh & Partner | Coatbridge Health Centre 1 Centre Pk Court | 2011-05-17
Coatbridge | 61485 | Dr. Flanigan & Partners | 7 Church Street Coatbridge | 2011-05-17
Carnwath | 62351 | Drs. Tiley & Ward | The Health Centre 7 Biggar Rd Carnwath, ML11 8HJ | 2011-05-24
Cumbernauld | 61305 | Dr. Nahar & Partners | Kildrum Health Centre Afton Rd Cumbernauld | 2011-05-24
Cumbernauld | 61324 | Dr. Handa & Partners | Condorrat Health Centre 16 Airdrie Rd Cumbernauld | 2011-05-31
Cumbernauld | 61324 - Branch site | Dr Handa & Partners | 32 Smithyends, Cumbernauld Village | 2011-05-31
Cumbernauld | 61381 | Drs. Gillani & Clifford | Abronhill Health Centre Pine Rd Abronhill | 2011-06-07
Hamilton | 63442 | Oak Lodge | Oak Lodge Medical Practice 32 Miller St Hamilton | 2011-06-07
East Kilbride | 63231 | Dr. I.C. Campbell & Partners | Hunter Health Centre Andrew St E.K. | 2011-06-14
East Kilbride | 63245 | Dr. McTosh & Partners | Hunter Health Centre Andrew St E.K. | 2011-06-14
East Kilbride | 63250 | Dr. Docherty & Partners | Hunter Health Centre Andrew St E.K. | 2011-06-21
East Kilbride | 63264 | Huntergreen | Hunter Health Centre Andrew St E.K. | 2011-06-21
East Kilbride | 63283 | Drs. Simmons & Cooper | Hunter Health Centre Andrew St E.K. | 2011-06-28
East Kilbride | 63298 | Dr. McTaggarts & Partners | Hunter Health Centre Andrew St E.K. | 2011-06-28
Hamilton | 63481 | Dr. Tansey & Partners | Low Waters Medical Centre Mill Rd Hamilton | 2011-07-05
Hamilton | 63423 | Dr. Dobbie & Partners | 51 Portland Park Hamilton | 2011-07-05
Harthill | 62844 | Harthill Health Centre | Harthill Health Centre 24-26 Victoria St Harthill | 2011-07-12
Holytown | 62120 | Drs. O'Keefe & Rao | 43-45 Main Street Holytown | 2011-07-12
Kilsyth | 61502 | Dr. Walker & Partner (now Kilsyth Medical Partnership) | The Health Centre Burngreen Kilsyth | 2011-07-19
Kirkmuirhill | 62613 | Dr. M. Idrees | 45 Thornton Road Kirkmuirhill | 2011-07-26
Kirkmuirhill | 62628 | Dr. Bowman | 125 Carlisle Road Blackwood ML11 9RT | 2011-07-26
Lanark | 62238 | Dr. Criggie & Partners | Lanark Health Centre Sth Vennell Lanark | 2011-08-02
New Stevenson | 62045 | Dr. McKibben & Partners | 120 Stevenson st , Newstevenson | 2011-08-09
Newarthill | 62115 | Dr. K. Menon | 15 Carfin Road Newarthill | 2011-08-09
Newarthill | 63546 | Dr C MacInnes | 60-64 High Street, Newarthill | 2011-08-16
Newarthill | 63546 - Branch | Dr. D.C. MacInnes & Partners | 45 Main Street, Calderbank, ML6 9SG | 2011-08-16
Newmains | 62811 | Dr. Majumdar & Fisher | Newmains Health Centre 17 Manse Rd Newmains | 2011-08-23
Shotts | 62991 | Dr. Walimbe | 269 Station Rd, Dykehead, Shotts | 2011-08-23
Shotts | 62986 | Dr. MacFarlane & Partners | Shotts Health Centre 36 Station Rd, Shotts | 2011-08-30
Shotts | 62897 | Dr. George | Shotts Health Centre 36 Station Rd, Shotts | 2011-08-30
Strathaven | 63724 | Dr. C.M.C. Campbell & Partners | Strathaven Health Centre The Ward Strathaven | 2011-09-06
Strathaven | 63739 | Dr. Godley & Partners | The Avondale Medical Practice Strathaven | 2011-09-06
Newmains | 62830 | Drs. Reddy & Sethu Raman | Newmains Practice Manse Rd Newmains | 2011-09-13

## Proposed Migration Dates
Year | Month | Date | Day | Comment
2010 | April | 2nd | Friday
2010 | April | 5th | Monday
2010 | May | 3rd | Monday | GP Only
2010 | May | 31st | Monday
2010 | July | 19th | Monday | GP Only
2010 | September | 24th | Friday
2010 | September | 27th | Monday
2010 | December | 27th | Monday
2010 | December | 28th | Tuesday
2011 | January | 3rd | Monday
2011 | January | 4th | Tuesday
2011 | April | 2nd
2011 | April | 5th
2011 | May | 3rd
2011 | May | 31st
2011 | July | 19th
2011 | September | 27th
2011 | September | 28th
2011 | December | 27th
2011 | December | 28th

## Updated Migration Plan
Note on AN49: Lynn Connell
Note on AN50: Lynn Connell
Note on AN51: Lynn connell
Note on AN53: Lynn connell
Note on AN54: Lynn Connell
Note on AN83: Richard Harrison
Note on AN85: Lynn Connell
Note on AN93: Helen McLean
Note on AN99: Caryl Jones
Note on AN100: Helen McLean
Note on AN101: Lynn Connell
Note on AN103: Lynn Connell
Note on AN106: Richard Harrison (was Lynn Connell)
Note on AN107: Caryl Jones
Note on AN108: Caryl Jones
Note on AN109: Lynn Connell
Note on AP1: Darren Hanrahan: elaine.henderson@isd.csa.scot.nhs.uk
Note on AT49: Richard Harrison
Note on AT50: Helen McLean
Note on AT51: Brian Cripps
Note on AT53: Amanda McKay
Note on AT54: Lynn Connell
Note on AT83: Debbie Cuthbert
Note on AT85: Lynn connell
Note on AT93: Helen McLean
Note on AT99: Amanda McKay & Richard Harrison
Note on AT100: Lynn Connell
Note on AT101: Brian Cripps
Note on AT103: Brian Cripps
Note on AT106: Helen McLean
Note on AT107: Helen McLean
Note on AT108: Helen McLean
Note on AT109: Brian Cripps
Note on AU49: Richard Harrison
Note on AU50: Helen McLean
Note on AU51: Brian Cripps
Note on AU53: Amanda McKay
Note on AU54: Lynn Connell
Note on AU83: Debbie Cuthbert
Note on AU85: Lynn connell
Note on AU93: Helen McLean
Note on AU99: Amanda McKay & Richard Harrison
Note on AU100: Lynn connell
Note on AU101: Brian Cripps
Note on AU103: Brian Cripps
Note on AU106: Helen McLean
Note on AU107: Helen McLean
Note on AU108: Helen McLean
Note on AU109: Brian Cripps
Note on AV49: Richard Harrison
Note on AV51: Brian Cripps
Note on AV53: Amanda McKay
Note on AV54: Lynn Connell
Note on AV85: Lynn connell
Note on AV99: Amanda McKay & Richard Harrison
Note on AV100: Lynn connell
Note on AV103: Brian Cripps Date of 23rd confirmed with practice… to be used as a follow-up training day
Note on AV106: Helen McLean
Note on AV107: Helen McLean
Note on AW53: Amanda McKay
Note on AW54: Lynn Connell
Note on AW85: Lynn connell
Note on AW99: Amanda McKay & Richard Harrison
Note on AW100: Lynn Connell
Note on AW106: Helen McLean
Note on AW107: Helen McLean
Note on BA14: Install Engineer: Phil Mullen 3rd May Bank Holiday
Note on BA20: Install Engineer: Ian Rannie & Barella
Note on BA28: Install Engineer: Phil Mullen
Note on BA49: Phil Mullen
Note on BA50: Ian Rannie
Note on BA51: Phil Mullan
Note on BA53: Ian Rannie
Note on BA54: Ian Rannie
Note on BA77: Install Engineer: Phil Mullen & Ian Rannie
Note on BA83: Ian Rannie
Note on BA85: Phil Mullen
Note on BA93: Philip Mullen
Note on BA99: Dave Barella
Note on BA100: Phil Mullen
Note on BA101: Phil Mullen
Note on BA103: Bainton Gary:
Note on BA106: Phil Mullen
Note on BA107: Ian Rannie
Note on BA108: Ian Rannie
Note on BA109: David Barella
Note on BC49: Helen McLean
Note on BC50: Brian Cripps
Note on BC51: Helen McLean
Note on BC53: Amanda McKay
Note on BC54: Brian Cripps
Note on BC83: Debbie Cuthbert
Note on BC85: Amanda McKay
Note on BC93: Richard Harrison
Note on BC99: Richard Harrison
Note on BC100: Richard Harrison
Note on BC101: Brian Cripps
Note on BC103: Brian Cripps
Note on BC106: Helen McLean
Note on BC107: Helen McLean
Note on BC108: Helen McLean
Note on BC109: Lynn Connell
Note on BD49: Helen McLean
Note on BD50: Brian Cripps
Note on BD51: Helen McLean
Note on BD53: Amanda McKay
Note on BD54: Brian Cripps
Note on BD83: Debbie Cuthbert
Note on BD85: Amanda McKay
Note on BD93: Richard Harrison
Note on BD99: Richard Harrison
Note on BD100: Richard Harrison
Note on BD101: Brian Cripps
Note on BD103: Brian Cripps
Note on BD106: Helen McLean
Note on BD107: Helen McLean
Note on BD108: Helen McLean
Note on BD109: Lynn Connell
Note on BE49: Helen McLean
Note on BE50: Brian Cripps
Note on BE51: Helen McLean
Note on BE53: Amanda McKay
Note on BE54: Brian Cripps
Note on BE83: Debbie Cuthbert
Note on BE85: Amanda McKay
Note on BE93: Richard Harrison
Note on BE99: Richard Harrison
Note on BE100: Richard Harrison
Note on BE101: Brian Cripps
Note on BE103: Brian Cripps
Note on BE106: Helen McLean
Note on BE107: Helen McLean
Note on BE108: Helen McLean
Note on BE109: Lynn Connell
Note on BF53: Amanda McKay
Note on BF54: Brian Cripps
Note on BF85: Amanda McKay
Note on BF101: Brian Cripps
Note on BI20: mccaulm: Second Pathology date was previously 28th Apr.
Note on BI49: Richard Harrison
Note on BI50: Brian Cripps & Richard Harrison
Note on BI51: Helen McLean & Richard Harrison
Note on BI53: Helen McLean
Note on BI54: Brian Cripps
Note on BI83: Richard Harrison
Note on BI85: Debbie Cuthbert
Note on BI93: Richard Harrison
Note on BI99: Richard Harrison
Note on BI100: Debbie Cuthbert & Richard Harrison
Note on BI101: Helen McLean & Debbie Cuthbert
Note on BI103: Brian Cripps & Debbie Cuthbert
Note on BI106: Helen McLean
Note on BI107: Richard Harrison
Note on BI108: Helen McLean
Note on BI109: Debbie Cuthbert
Note on BJ49: Helen McLean
Note on BJ50: Helen McLean
Note on BJ51: Helen McLean & Richard Harrison
Note on BJ53: Helen McLean
Note on BJ54: Brian Cripps & Helen McLean
Note on BJ83: Richard Harrison
Note on BJ85: Debbie Ctuhbert & Helen McLean
Note on BJ93: Helen McLean
Note on BJ99: Richard Harrison
Note on BJ100: Helen McLean & Richard Harrison
Note on BJ101: Amanda McKay & Helen McLean
Note on BJ103: Debbie Cuthbert & Helen McLean
Note on BJ106: Helen McLean
Note on BJ107: Amanda McKay
Note on BJ108: Richard Harrison
Note on BJ109: Helen McLean & Debbie Cuthbert